## Sheet1
Week: | Day: | To Be Done: | Notes: | Complete Date:
Week 1: | Tuesday | Meet with James
| Wednesday | Research Project Proposal | Make new sheet in Excel | 2019-03-27
Week 2: | Tuesday | Meet with James/ have prop 1 done
| Wednesday | Start work on 2nd prop |  | 2019-04-03
Week 3: | Tuesday | Meet with James/have prop 2 done
| Wednesday | Start work on 3rd prop |  | 2019-04-10
Week 4: | Tuesday | Meet with James/ have prop 3 done
| Wednesday | Start work on 4th prop |  | 2019-04-17
Week 5: | Tuesday | Meet with James/ have prop 4 done
| Wednesday | Start work on 5th prop |  | 2019-04-24
Week 6: | Tuesday | Meet with James/ have prop 5 done
| Wednesday | Start work on 6th prop |  | 2019-05-01
Week 7: | Tuesday | Meet with James/ have prop 6 done
| Wednesday | Start work on 7th prop |  | 2019-05-08
Week 8: | Tuesday | Meet with James/ have prop 7 done
| Wednesday | Start work on 8th prop |  | 2019-05-15
Week 9: | Tuesday | Meet with James/ have prop 8 done
| Wednesday | Start work on 9th prop |  | 2019-05-22
Week 10: | Tuesday | Meet with James/ have prop 9 done
Put eveything together in one scene